## UserStoryDeliverable
ID | Theme | As a/an | I want to… | so that… | Notes | Acceptance Criteria / Conditions of Satisfaction | Priority | Status
1 | Investing | User | Access current stock prices | I can be informed about the current state of the market | Gold/bond/commodity markets may be included, it depends on the API. Something to keep in mind | We can access stock prices (w/ historical data) via an API and we can display this information via a graph | Must have | Incomplete
2 | Investing | User | Track specific stocks | I can be informed about the stocks that I care about |  | We allow the user to select certain stocks which are saved in the database and are prominently displayed after login | Must have | Incomplete
3 | Financial Management | User | Track and manage the value of different assets | I can be informed about my financial life | Might also include crypto or other currencies | We allow the user to input different assets (houses, cars, stocks, etc.) along with their estimated value | Must have | Incomplete
4 | Financial Management | User | Have my currently invested stocks automatically update my net worth | I can be informed about my financial life |  | The current value of the stock is automatically added/subtracted to the user's net worth | Should have | Incomplete
5 | Financial Management | User | Track and manage various income streams | I can be informed about my financial life |  | We allow the user to input different recurring income streams (such as paychecks) | Must have | Incomplete
6 | Financial Management | User | Track and manage various expenses | I can be informed about my financial life |  | We allow the user to input different recurring expenses (such as bills) and one-off expenses (such as groceries) | Must have | Incomplete
7 | Financial Management | User | Search my imputed incomes, assets and expenses | I can easily find important information about my financial life |  | We allow the user to search their incomes, assets and expenses, either by name or date (w/ a range) | Should have | Incomplete
8 | Financial Management | User | Visualize my various incomes, assets and expenses in a graph | I can easily visualize information about my financial life |  | We graph financial information over a various timeframes | Could have | Incomplete
9 | Financial Management | User | See my current net worth | I can easily see my overall financial position |  | We add assets and incomes and subtract expenses, and prominently display the result | Must have | Incomplete
10 | Financial Management | User | Toggle different incomes, assets and expenses on and off | I can experiment with and better understand my current financial position |  | We allow the user to toggle on/off their different incomes, assets and expenses, with this affecting their displayed net worth and graphs | Could have | Incomplete
11 | Financial Management | User | See what percentage a certain income or asset is of my total net worth | I can better understand my current financial position |  | We display a pie chart with every income and asset being a slice. When they hover over each slice, the slice is highlighted and information is displayed | Could have | Incomplete
12 | Financial Management | User | Set different financial goals surrounding my net worth | I can work towards my life goals |  | We allow the user to input their goals with their net worth (such as double net worth in a month). We have reminders and celebrate when the user succeeds | Could have | Incomplete
13 | Financial Management | User | Set different financial goals surrounding my income | I can work towards my life goals |  | We allow the user to input their goals with their income (such as making $1000/week within year). We have reminders and celebrate when the user succeeds | Could have | Incomplete
14 | Financial Management | User | Categorize my different incomes, assets and expenses | I can better understand my current financial position | Maybe use AI? | We (either automatically or make the user tag) have each income, asset and expense fall into a specific category and display it | Should have | Incomplete
15 | Financial Management | User | Receive warnings when my expenses cost more than my income | I can avoid overspending |  | When expenses are more than income streams, warn user with popup | Could have | Incomplete
16 | Investing | User | Access current crypto prices | I can be informed about the cryptocurrency that I care about |  | We can access crypto prices (w/ historical data) via an API and we can display this information via a graph | Could have | Incomplete
17 | Investing | User | Access current foreign currency prices | I can be informed about the foreign currencies that I care about |  | We can access foreign currency prices (w/ historical data) via an API and we can display this information via a graph | Could have | Incomplete
18 | Profile | User | Change my profile picture | I can personalize my financial account |  | We allow the user to upload a profile picture and store it in our database | Should have | Incomplete
19 | Profile | User | Change the theme of the website | I can personalize my financial account |  | We have multiple website themes and change them based on user input, remembering their last choice | Could have | Incomplete
20 | Profile | User | Change my display name | I can personalize my financial account |  | We have a seperate user name field and that the user can change | Could have | Incomplete
21 | Security | User/Developer | Have a secure website | My financial data is secure |  | We have strict password requirements and we encrypt any financial data | Must have | Incomplete
22 | Security | User | Easily log into the website via Google sign-in | I do not need to type in my password every time I want to access the website |  | We connect with Google sign-in, allowing the user to log in with a Google account | Could have | Incomplete
23 | News | User | Access the latest financial news | I can stay informed about my investments |  | We display the headlines of new financial articles and provide links for user's to read more | Could have | Incomplete
24 | AI | User | Have AI analyze my financial information and give suggestions | I can optimize my financial strategy | We might want to consider running a local AI. We also need to consider speed. Maybe initialize AI during login? | We have an AI-powered chatbot that reads financial information and gives relevant suggestions | Should have | Incomplete
25 | Simulation | User | Run simulations with my financial information | I can understand potential future financial outcomes | https://en.wikipedia.org/wiki/Monte_Carlo_method We also need to figure out what factors will affect the simulation | We have a Monte Carlo simulation based on various possible outcomes and return the result | Should have | Incomplete
26 | Simulation | User | Track my simulation runs over time | Assess how different decisions affect outcomes |  | We save the results of previous Monte Carlo simulations and allow the user to view them | Could have | Incomplete
27 | Profile | User | Decide what graphs are being displayed | I can personalize my financial account |  | We allow the user to drag/drop different graphs containing different information | Could have | Incomplete
28 | Simulation | User | Run simulations based on different possible outcomes | I can better understand my current financial position |  | We have allow the user to affect the Monte Carlo simulation based on different profiles (such as bear/bull market for example) | Could have | Incomplete
29 | Financial Management | User | See how diverse my portfolio is | I can better understand my current financial position | https://www.swanglobalinvestments.com/the-mathematics-of-diversification/ | We calculate and display how diverse the user's finances are | Could have | Incomplete
30 | Financial Management | User | See how well I am following various budgeting strategies | I can work towards my life goals | https://srfs.upenn.edu/financial-wellness/browse-topics/budgeting/popular-budgeting-strategies | We allow the user to select a budgeting strategy from a list and measure how close they are following their selected strategy | Could have | Incomplete
31 | Simulation | User | Run simulations in a reasonable amount of time | I do not have to wait for the simulation |  | We optimize the simulation so that it runs in a reasonable amount of time (sub 10 seconds) | Should have | Incomplete